## Sheet1
REF / ID | PRE - MITIGATION |  |  |  | DEPARTMENT / LOCATION | MITIGATIONS / WARNINGS / REMEDIES | POST - MITIGATION
| RISK | RISK SEVERITY (PRE) | RISK LIKELIHOOD (PRE) | RISK LEVEL (PRE) |  |  | RISK SEVERITY (POST) | RISK LIKELIHOOD (POST) | RISK LEVEL (POST) | ACCEPTABLE TO PROCEED? (Y/N)
R-01 | Unauthorized access to patient data (weak RBAC / privilege escalation) | INTOLERABLE | POSSIBLE | EXTREME | Security / Backend | Enforce RBAC + least privilege; MFA for Admin/Doctor; strong password policy; session timeout; audit logs; periodic access review. | TOLERABLE | IMPROBABLE | MEDIUM | YES
R-02 | Data breach due to insecure storage of prescriptions/medical history | INTOLERABLE | POSSIBLE | EXTREME | Security / Storage | Encrypt data at rest and in transit (TLS); secure bucket policies; private links; key rotation; vulnerability scans; periodic security review. | TOLERABLE | IMPROBABLE | MEDIUM | YES
R-03 | Broken authentication (token hijacking / weak JWT handling) | UNDESIRABLE | POSSIBLE | HIGH | Backend / Auth | Short-lived access token + refresh token; secure HttpOnly cookies; rotate secrets; validate token expiry/signature; logout invalidation. | TOLERABLE | IMPROBABLE | LOW | YES
R-04 | Appointment double-booking due to race conditions | UNDESIRABLE | POSSIBLE | HIGH | Backend / Appointments | Atomic slot locking; DB transactions; unique constraint on (doctorId, slot); idempotent booking API; concurrency tests. | TOLERABLE | IMPROBABLE | LOW | YES
R-05 | Wrong slot availability shown (cached/old data) | TOLERABLE | POSSIBLE | MEDIUM | Backend + UI | Use real-time slot refresh; short cache TTL; server-side final availability check; show conflict message and alternate slots. | ACCEPTABLE | IMPROBABLE | LOW | YES
R-06 | Prescription upload failure (network interruption / timeout) | TOLERABLE | POSSIBLE | MEDIUM | Frontend / Upload Service | Resumable uploads; chunk upload; retry with backoff; progress UI; increase timeout safely; background queue. | ACCEPTABLE | IMPROBABLE | LOW | YES
R-07 | Malicious file upload (malware in PDF/image) | INTOLERABLE | POSSIBLE | EXTREME | Security / Upload | Allow-list file types; size limits; antivirus scanning; PDF sanitization; store in isolated bucket; scan before doctor access. | TOLERABLE | IMPROBABLE | MEDIUM | YES
R-08 | OCR extraction errors causing wrong medicine details | UNDESIRABLE | POSSIBLE | HIGH | AI/OCR Module | Confidence threshold; highlight uncertain fields; human verification; allow manual correction; store original prescription; test with diverse samples. | TOLERABLE | POSSIBLE | MEDIUM | YES
R-09 | Automated follow-up call fails due to provider outage (Twilio/Vapi) | TOLERABLE | POSSIBLE | MEDIUM | Automation / Integrations | Provider fallback; circuit breaker; queued retries; notify via SMS/Email when call fails; monitoring + alerting. | ACCEPTABLE | IMPROBABLE | LOW | YES
R-10 | Notification not delivered (SMS/Email gateway issue) | TOLERABLE | POSSIBLE | MEDIUM | Notification Service | Delivery status tracking; retry policy; alternate channel (push/email/SMS); message logs; show confirmation in app. | ACCEPTABLE | IMPROBABLE | LOW | YES
R-11 | Doctor verification fraud (fake license/certificates) | INTOLERABLE | POSSIBLE | EXTREME | Admin / Verification | Manual review checklist; authenticity checks; cross-check license where possible; audit trail; re-verification schedule. | UNDESIRABLE | IMPROBABLE | MEDIUM | YES
R-12 | Unauthorized medical history access (privacy breach) | INTOLERABLE | POSSIBLE | EXTREME | Security / Data Access | Consent-based access; doctor access only for assigned appointment/patient; strict RBAC; access logs; alerts for suspicious access. | TOLERABLE | IMPROBABLE | MEDIUM | YES
R-13 | Data loss due to missing backups or accidental deletion | UNDESIRABLE | POSSIBLE | HIGH | Database / Storage | Automated backups; point-in-time recovery; retention policy; replication; delete protection; periodic restore drills. | TOLERABLE | IMPROBABLE | LOW | YES
R-14 | Performance degradation under peak load (booking/upload spikes) | UNDESIRABLE | POSSIBLE | HIGH | Backend / Infrastructure | Indexing + pagination; caching; async processing; autoscaling; load testing; rate limiting; optimize queries. | TOLERABLE | POSSIBLE | MEDIUM | YES
R-15 | AI chatbot gives unsafe/incorrect medical advice | INTOLERABLE | POSSIBLE | EXTREME | AI Assistant | Medical disclaimer; restrict to general guidance; confidence gating; escalate to doctor; safe-response rules; feedback & monitoring. | UNDESIRABLE | IMPROBABLE | MEDIUM | YES