## WBS
AI-Powered Smart Healthcare Assistant System · Work Breakdown Structure
WBS ID | Lvl | Work Package / Task | Phase | Days | Start Wk | End Wk | Deliverable
1 | 1 | PROJECT INITIATION | Initiation | 10 | 1 | 2 | Project Charter
1.1 | 2 | Requirement Gathering & Stakeholder Analysis | Initiation | 5 | 1 | 1 | Stakeholder Register
1.2 | 2 | Feasibility Study | Initiation | 3 | 1 | 1 | Feasibility Report
1.3 | 2 | Project Charter & Scope Definition | Initiation | 2 | 2 | 2 | Project Charter
2 | 1 | PROJECT PLANNING | Planning | 14 | 2 | 5 | Project Plan
2.1 | 2 | SRS Document (IEEE Format) | Planning | 5 | 2 | 3 | SRS Document
2.2 | 2 | System Architecture Design | Planning | 4 | 3 | 4 | Architecture Diagram
2.3 | 2 | WBS, Cost & Schedule Estimation | Planning | 3 | 4 | 5 | Project Schedule
2.4 | 2 | Risk Management Plan | Planning | 2 | 5 | 5 | Risk Register
3 | 1 | SPRINT 1 – CORE BACKEND & AUTH | Development | 28 | 1 | 5 | Auth Module
3.1 | 2 | User Authentication Module | Development | 7 | 1 | 2 | Auth API
3.1.1 | 3 | Registration & Login (JWT) | Development | 3 | 1 | 2 | Auth Endpoints
3.1.2 | 3 | Role-Based Access Control | Development | 2 | 2 | 2 | RBAC Middleware
3.1.3 | 3 | Email / OTP Verification | Development | 2 | 2 | 3 | Verification Service
3.2 | 2 | Doctor Verification Module | Development | 7 | 3 | 4 | Verification Dashboard
3.2.1 | 3 | Document Upload & Storage | Development | 3 | 3 | 4 | Upload Service
3.2.2 | 3 | Admin Review & Approval Workflow | Development | 4 | 4 | 5 | Admin Dashboard
3.3 | 2 | Database Schema & Setup (MongoDB) | Development | 5 | 4 | 5 | DB Schema
3.4 | 2 | Sprint 1 Testing & QA | Testing | 4 | 5 | 5 | Test Report 1
4 | 1 | SPRINT 2 – APPOINTMENTS & PRESCRIPTIONS | Development | 30 | 5 | 9 | Booking & Rx Module
4.1 | 2 | Appointment Booking System | Development | 10 | 5 | 7 | Booking Module
4.1.1 | 3 | Doctor Search & Filter | Development | 3 | 5 | 6 | Search API
4.1.2 | 3 | Real-Time Slot Management | Development | 4 | 6 | 7 | Slot Service
4.1.3 | 3 | Reschedule / Cancel Logic | Development | 3 | 7 | 8 | Booking API
4.2 | 2 | Prescription Management | Development | 8 | 7 | 9 | Prescription Module
4.2.1 | 3 | File Upload (AES-256 Encrypted) | Development | 3 | 7 | 8 | Upload Endpoint
4.2.2 | 3 | OCR Text Extraction | Development | 3 | 8 | 9 | OCR Service
4.2.3 | 3 | Sharing & Expiry Notifications | Development | 2 | 9 | 9 | Notification Trigger
4.3 | 2 | Medical History Module | Development | 7 | 8 | 10 | History API
4.3.1 | 3 | Chronological Records View | Development | 3 | 8 | 9 | History Endpoint
4.3.2 | 3 | Filter, Export PDF, Audit Log | Development | 4 | 9 | 10 | Export Service
4.4 | 2 | Frontend – React.js Patient Dashboard | Development | 8 | 8 | 10 | Patient UI
4.5 | 2 | Sprint 2 Testing & QA | Testing | 5 | 10 | 11 | Test Report 2
5 | 1 | SPRINT 3 – AI CHATBOT, AUTOMATION & ADMIN | Development | 28 | 9 | 13 | Complete System
5.1 | 2 | AI Chatbot (Gemini API) | Development | 8 | 9 | 11 | Chatbot Module
5.1.1 | 3 | NLP Query Processing | Development | 4 | 9 | 10 | Chatbot API
5.1.2 | 3 | Session Context & FAQ Engine | Development | 4 | 10 | 11 | Context Manager
5.2 | 2 | Follow-Up Automation (Twilio + Vapi + n8n) | Development | 8 | 11 | 12 | Automation Module
5.2.1 | 3 | Medication Reminder Scheduler (n8n) | Development | 3 | 11 | 12 | Workflow Automation
5.2.2 | 3 | AI Voice Follow-Up Calls (Vapi) | Development | 3 | 12 | 12 | Voice Call Service
5.2.3 | 3 | SMS Notifications (Twilio) | Development | 2 | 12 | 13 | SMS Service
5.3 | 2 | Admin Dashboard | Development | 6 | 12 | 13 | Admin Panel
5.4 | 2 | Frontend – Doctor & Admin Dashboards | Development | 7 | 12 | 13 | Doctor/Admin UI
5.5 | 2 | Sprint 3 Testing & QA | Testing | 5 | 13 | 13 | Test Report 3
6 | 1 | INTEGRATION, SECURITY & PERFORMANCE | Testing | 9 | 12 | 13 | Tested System
6.1 | 2 | Integration Testing (All Modules) | Testing | 4 | 12 | 13 | Integration Report
6.2 | 2 | Security Audit (HIPAA / GDPR) | Testing | 3 | 13 | 13 | Security Report
6.3 | 2 | Performance & Load Testing | Testing | 2 | 13 | 13 | Perf Report
7 | 1 | DEPLOYMENT & PROJECT CLOSURE | Deployment | 8 | 12 | 13 | Live System
7.1 | 2 | Cloud Deployment (AWS / Docker / K8s) | Deployment | 4 | 12 | 13 | Deployed App
7.2 | 2 | User Documentation & Training | Deployment | 2 | 13 | 13 | User Manuals
7.3 | 2 | Project Review & Handover | Deployment | 2 | 13 | 13 | Closure Report
PHASE LEGEND
Initiation | Planning | Development | Testing | Deployment

## Cost Estimation
AI-Powered Smart Healthcare Assistant System · Cost Estimation (3-Month Project)
Estimation Method | COCOMO II + FPA | Project Duration | 3 Months | Model Type | Semi-Detached
A. Function Point Analysis (FPA)
Function Type | Count | Complexity | Weight | FP Score | Example Functions
External Inputs (EI) | 8 | Average | 4 | 32 | Login, Register, Book Appt, Upload Rx ×4
External Outputs (EO) | 7 | Average | 5 | 35 | Reports, Confirmations, Notifications ×3, PDF Export ×2
External Inquiries (EQ) | 6 | Average | 4 | 24 | Doctor Search, History View, Chatbot, Slot Check ×3
Internal Logical Files (ILF) | 7 | Average | 10 | 70 | Users, Doctors, Appts, Prescriptions, History, Reminders, ChatLogs
External Interface Files (EIF) | 5 | Average | 7 | 35 | Twilio, Vapi, Gemini API, n8n, MongoDB Atlas
Unadjusted Function Points (UFP) |  |  | 196 |  | Sum of all weighted function points
Value Adjustment Factor (VAF) | 0.95 | Healthcare domain complexity adjustment
Adjusted Function Points (AFP) | 186.2 | AFP = UFP × VAF
B. COCOMO II – Semi-Detached Model
Parameter | Symbol | Formula / Source | Value | Unit | Notes
Lines of Code Estimate | 9.8686 | AFP×53÷1000 |  | KLOC | 53 LOC/FP for Node.js / React stack
COCOMO Coefficient | 3 | 3.0 (semi-det.) |  | — | Semi-detached project mode
COCOMO Exponent | 1.12 | 1.12 (semi-det.) |  | — | Semi-detached project mode
Raw Effort E = a × KLOC^b | 38.9661 | a × KLOC^b |  | PM | Person-months (unadjusted)
Development Time D = 2.5×E^0.38 | 10.0554 | 2.5 × E^0.38 |  | Months | Derived project duration
Avg Team Size P = E÷D | 3.8751 | E ÷ D |  | People | Ideal staffing level
Effort Adj. Factor (EAF) | 0.88 | RELY×DATA×CPLX |  | — | Adjusted for 3-month scope
Adjusted Effort E_adj = E×EAF | 34.2902 | E × EAF |  | PM | Final effort estimate
C. Staffing & Resource Plan (3-Month Project)
Role | No. of People | Monthly Rate (₹) | Duration (Months) | Total Cost (₹) | Responsibility
Project Manager | 1 | 60000 | 3 | 180000 | Planning, coordination, reporting
Full-Stack Developer (Node + React) | 2 | 55000 | 3 | 330000 | Core backend APIs + frontend UI
AI / ML Integration Developer | 1 | 50000 | 2 | 100000 | Gemini API, Vapi, chatbot integration
QA / Test Engineer | 1 | 38000 | 2 | 76000 | Test cases, regression, security checks
DevOps / Cloud Engineer | 1 | 48000 | 1 | 48000 | AWS deployment, Docker, CI/CD pipeline
UI / UX Designer | 1 | 35000 | 1 | 35000 | Wireframes, design system, prototypes
Total Personnel Cost |  |  |  | 769000
D. Total Project Cost Summary
Cost Category | Amount (₹) | 3-Mo. Rate | Qty | Calculated | Notes
Personnel Costs | 769000 |  |  |  | Team salaries – 3 months (see Section C)
Cloud & Infrastructure | 45000 | 15000 | 3 |  | AWS EC2 + S3 + MongoDB Atlas – ₹15,000/mo
Third-Party API Costs | 21000 | 7000 | 3 |  | Twilio + Vapi + Gemini API – ₹7,000/mo
Software Licenses & Tools | 12000 |  |  |  | IDEs, PM tools, testing frameworks (one-time)
QA & Security Audit | 15000 |  |  |  | Basic pen test + HIPAA checklist review
Training & Documentation | 8000 |  |  |  | User guides, internal onboarding
Contingency Reserve (10%) | 87000 |  |  |  | 10% risk buffer on all categories above
TOTAL ESTIMATED PROJECT COST | 957000

## Gantt Chart
AI-Powered Smart Healthcare Assistant System · Project Gantt Chart (13 Weeks / 3 Months)
[5 empty] | Month 1 – March / April 2026 |  |  |  | Month 2 – April / May 2026 |  |  |  | Month 3 – May / June 2026
WBS | Task / Work Package | Phase | Owner | Days | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
1 | PROJECT INITIATION | Initiation | Team | 10
1.1 | Requirement Gathering | Initiation | All | 5
1.2 | Feasibility Study | Initiation | PM | 3
1.3 | Project Charter | Initiation | PM | 2
2 | PROJECT PLANNING | Planning | Team | 14
2.1 | SRS Document (IEEE) | Planning | All | 5
2.2 | System Architecture | Planning | Dev Lead | 4
2.3 | WBS, Cost & Schedule | Planning | PM | 3
2.4 | Risk Management Plan | Planning | PM | 2
3 | SPRINT 1 – CORE BACKEND & AUTH | Development | Dev Team | 28
3.1 | User Authentication (JWT/RBAC/OTP) | Development | Dev 1 | 7
3.2 | Doctor Verification Module | Development | Dev 2 | 7
3.3 | Database Schema (MongoDB) | Development | DBA | 5
3.4 | Sprint 1 Testing & QA | Testing | QA | 4
4 | SPRINT 2 – APPOINTMENTS & PRESCRIPTIONS | Development | Dev Team | 30
4.1 | Appointment Booking System | Development | Dev 1+2 | 10
4.2 | Prescription Management (Upload+OCR) | Development | Dev 1 | 8
4.3 | Medical History Module | Development | Dev 2 | 7
4.4 | React.js Patient Dashboard | Development | Frontend | 8
4.5 | Sprint 2 Testing & QA | Testing | QA | 5
5 | SPRINT 3 – AI CHATBOT & AUTOMATION | Development | Dev Team | 28
5.1 | AI Chatbot (Gemini API) | Development | AI Dev | 8
5.2 | Follow-Up Automation (Twilio+Vapi+n8n) | Development | Dev 3 | 8
5.3 | Admin Dashboard + Frontends | Development | Dev 2 | 7
5.5 | Sprint 3 Testing & QA | Testing | QA | 5
6 | INTEGRATION, SECURITY & DEPLOYMENT | Testing | QA+DevOps | 9
6.1 | Integration & Load Testing | Testing | QA | 4
6.2 | Security Audit (HIPAA/GDPR) | Testing | Security | 3
7 | DEPLOYMENT & PROJECT CLOSURE | Deployment | DevOps | 8
7.1 | Cloud Deploy (AWS/Docker/K8s) | Deployment | DevOps | 4
7.2 | Docs, Training & Handover | Deployment | PM+Dev | 4
PHASE LEGEND
Initiation | Planning | Development | Testing | Deployment

## Effort Summary
Effort Distribution by Phase · 3-Month Project
Phase | Tasks | Effort (PM) | Duration (Wks) | Team Size | Milestone
Initiation | 4 | 1 | 1 | 4 | Project Charter signed
Planning | 5 | 1.5 | 2 | 4 | SRS + Architecture approved
Sprint 1 | 4 | 4.5 | 3 | 5 | Auth & Verification modules live
Sprint 2 | 5 | 6.5 | 4 | 5 | Booking, Rx & History complete
Sprint 3 | 5 | 6.5 | 3 | 4 | Chatbot & Automation deployed
Testing | 4 | 3.5 | 2 | 3 | Security audit passed
Deployment | 4 | 1.5 | 1 | 3 | Live on AWS; handover signed
TOTAL | 31 | 25 | 16 | 28 | System live & handed over